## Slide 1: Young Emerging Professional (YEP Lite) India Launch

## Slide 2
Certificate
Presentation
Skills
Team
Creation
Decision
Making
Welcome Video
5 minutes
130 minutes
130 minutes
130 minutes
Welcome Video by Pallavi
Young Emerging Professionals – India Launch
Y E P LITE
Learner Journey
Highlights
Competency Lessons via HMM
Launch for 6000 employees Pan India
Complete Learning Journey on Degreed
YEP LITE Certificate
Launch Mailer
Program Genesis
YEP LITE – Ready for Launch by May 2020 with 5 Milestones
Welcome Video by CHRO
3 Harvard MentorManage Modules
YEP Café – Virtual Touchpoint session – 90 Minutes
Eligibility – Employees at B2, C1 who are Individual
Contributors and non – people managers
Program Duration : 5 Weeks
YEP
Café

## Slide 3: Learner Experience
YEP Community Manager - Primarily responsible for driving and ensuring completion of Journey for respective BU’s, timely Communication and to drive weekly engagements for the community.
LBP – Will help drive the program along with Community Managers.
HRBP – To validate the list of pax and also evangelize the session within BU’s
Yam Jam sessions with BU Leaders
Yammer to enable participants to share program testimonials

## Slide 4: Next Steps
Chart: YEP PAN INDIA LAUNCH
| Sign - Off on Genesis | To Finalise Launch date | Identification of Target Pax | Validation of Target Pax | CHRO Program Launch Mail | Head L&D Welcome Mail | Orientation Calls with CM's | Orientation Calls with Pax | Roll out of YEP Program | YEP Café | Closure of Journey | Issue Certificates to Pax
Start date | 43962 | 43962 | 43962 | 43965 | 43966 | 43966 | 43964 | 43969 | 43969 | 43983 | 44001 | 44011
Duration | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 5 | 30 | 22 | 5 | 9
End date | 43965 | 43965 | 43965 | 43966 | 43967 | 43967 | 43965 | 43973 | 44000 | 44005 | 44006 | 44022